## Slide 1: Transformation Programme Report - SIP and Research Systems Programme (RSP) – September 2018
Overview
Headlines
RSP – Progress Overview
General progress report
High level plan
Key risks
Please note separate benefits presentation to follow

## Slide 2: Overview
Primary focus remains on process improvements, though KPI’s indicate that benefits are being realised (contained in 17/18 performance report)
Process Improvements
Better service
Reduced Costs
Predictable (quicker) timelines
Increased customer satisfaction
Invest in additional capability
meet challenge of reducing budget
Better Health Research
Deliverables
Benefits
Ambition
Indicative ‘progress ‘ line

## Slide 3: Headlines
RSP Programme - Amber
Currently addressing technical interface challenges as a priority
Signed CCN for Pega to continue until 8 Feb to deliver working CTIMPS solution
Business case completed and submitted to DHSC
SIP Programme - Green
Restructuring of Approvals Directorate
  Consultation ends w/c 19 Nov
Restructuring of Policy Directorate
  Consultation ends 22 Nov
Customer support implementation plan agreed
Customer Charter published - https://www.hra.nhs.uk/about-us/customer-charter
Volunteer recruitment
  Those waiting for an interview reduced from 137 to 39

## Slide 4: HRA – IRAS 2 – Project Summary w/e 2018-11-09
Customer Success | Schedule | Hrs. to Budget | Technical | Testing | Resource | Legal
Key Areas of Progress this Week
06/11 – Sprint Review completed
06/11 – Business readiness / route to live initial meeting
07/11 – Sprint 7 formally completed
07/11 – Phase 1.1 Sprint 8 start
MHRA interface specification draft submission delivered 08/11; Final version expected 14/11
05/11 – BGO interface to HARP not delivered; approach confirmed
Continued elaboration phase 1.1 sprint 9 user stories
Guardrails: 96% Compliant Rules; 99 Weighted Score
Key Areas Planned for Next Week
14/11 – MHRA interface specification targeted for initial submission targeted
16/11 – Date to be confirmed for HARP interface specification
14/11 – PA Meeting to discuss SSO / CPMS interfaces targeted
Continue build for Sprint 8
Sprint 9 user stories targeting Ready for 14/11
Overall Status
Key Issues and Risks
Issue (AMBER): Lack of agreed data catalogue and process preventing interface specifications from being generated. Impacting planned interface development
  Initial version approved (V4 24/10) to allow interface work on initial submission to start; however this is being subject to ongoing change and is not the full set of data
  Latest submission version updated and reissued 06/11
  Final version to address remaining interfaces, originally targeted 02/11 not delivered and no target date confirmed
Issue (AMBER): CWOW process discussions directly impacting previously elaborated user stories
  There will continue to be risk of change until the process discussions are concluded.
  This may introduce re-work and directly affect the achievable scope within the current plan
Sprint Progress (Functional)
Project Summary
Phase 1.1 (Sprint 8) – started 07/11
Misaligned milestones with MHRA and NIHR increase risk to completion within target timeframes
Data catalogue and process dependency missed – originally targeted 12/10 approved version (23/10) subject to ongoing change
Whilst the MHRA initial submission interface is underway, there are delays to the start of the HARP and CPMS equivalents
Final version data catalogue – targeted 02/11 remains undelivered with no target date, impacting start of full interface development
Pega team reduced in planned size for first 2 weeks until there is better clarity on the data catalogue impacting planned velocity

## Slide 5
Transformation Programme
Date: 21st November
Workstream | Status | Commentary
Research Systems Programme |  | See slide 3
HRA Approval - Integrated Process |  | Proceeding as planned
HRA Approval – Proportionality |  | Proceeding as planned
HRA Approval - Get it right first time |  | It is proposed that this project will formally close in November 2018, having monitored the performance of the verification tool for six-months after launch.
HRA Approval - Amendments |  | Challenges around resource remain, particularly as the Four Nations Policy Leads are keen to see this project move at pace. Draft triage tool produced which now needs to be reviewed and tested.
HRA Approval – Amendments (e-submission) |  | e-submission of amendments. Cannot be achieved in current timeline & unable to re-plan, dependency on developments in new IRAS
HRA Approval – Volunteer recruitment and management |  | Those waiting for an interview reduced from 137 to 39
PIER: Public involvement in the ethical review process leading to more favourable opinions and improved health research |  | Test bed (organisations who are testing the new Public Involvement guidance in IRAS) process/protocol finalised
Corporate: Development of an effective and efficient corporate support and infrastructure model that results in a business model that secures the best value ‘mix’ of in-house, third party and shared ALB resourcing. |  | Further work on developing ESR Function in progress (offers greater levels of automation/self service)
Customer Support: Delivering an integrated approach to managing the customer relationship, ensuring that all queries are managed effectively and that feedback is effectively used in improving service provision |  | Implementation plan agreed Customer Charter published
Overall
RAG
Budget

## Slide 6: Key Risks
 | Research Systems Programme | Mitigation | Trend
1 | Future running costs cannot be accommodated in HRA spending review allocation | Currently developing financial models for 19/20 against a number of possible scenarios | 
2 | The complexity of managing two supplier relationships whilst developing new IRAS, maintaining current IRAS and developing and maintaining HARP will increase pressure on team and potentially impact on level of service | Both suppliers are now engaged on programme and positive relationships are developing. The management of the relationship and the associated capacity and capability to manage the work going forward is being considered by the DD Research Systems and our Implementation partner | 
3 | Unable to deliver critical functionality and/or connectivity with MHRA necessary for CTR | Scheduled in meetings with MHRA, Appian, Pega and BGO to consider and develop technical solutions | 