## Slide 1
Performance report
Qtr2 2018/19
Oct 2018
Agenda item: 10D

## Slide 2: Contents
 | Slides
Executive summary | 3
Strategic update: KPIs, benefits, and projects | 4-16
Operational KPIs | 18-26
Finance report | Appendix - Incl in papers
HRA Approval assessment performance report | Appendix

## Slide 3: Executive summary
Championing research | Easier to do research | Proactive and strategic | Technology | Effective and adds value | Finance | Capacity
Strategic highlights
Approvals timelines consistently being met for all but non-rec studies
82% of applicants score our overall service highly
GAfREC implemented
New project set up to consider Sponsor level IG standards
Customer Charter published
New IRAS development progressing at pace, GFI approach agreed
Audit and Risk Committee assessment performed
Transparency awareness survey completed
Strategic challenges
Full research systems transformation requires accelerated investment to compete on global stage
Complex technology, multiple systems and stakeholders, increases delivery risk and potential delay
Select Committee report on transparency anticipated in Qtr3
Uncertainty around Brexit remains a key strategic priority, service delivery protected whatever the outcome
Budget pressures remain, £150k savings for 2018/19 secured, 2019/20 planning commenced.
Overall Performance

## Slide 4: Strategic update KPIs, benefits and projects

## Slide 5: Championing health and social care research
Theme | Description | Measure | Update
Transparency | Greater awareness of research registration, and in turn, increased rates of registration of clinical trials | Increase in awareness of the requirement to register clinical trials Increase in registration rate for clinical trials | Survey of awareness and practice closed with 268 responses, around a quarter from researchers – analysis underway to establish baseline for awareness.
Public involvement | Improvement in the number, quality and relevance of descriptions of public involvement in research applications for Approval | Increase in applications reporting public involvement at ethical review Increase in applications which have clearly involved patients, service users and the public in their development | 3 test beds signed up. PIER education items have been delivered at CAG away-day and South Central REC Regional Training Day. Measures being defined.

## Slide 6: Championing health and social care research
GAfRECs implemented 17 September 2018
Baseline for clinical trials registration rate established
Baseline for transparency awareness in development
House of Commons Science and Technology Committee published the first of two reports following its inquiry into research integrity. HRA gave oral and written evidence
Customer Charter published

## Slide 7: Making it easier to conduct high quality research in the UK
Theme | Description | Measure | Update
Streamlining processes for researchers | Our ability to predict how long a particular type of application will take to process based on the quality of application and complexity of study. | Percentage of studies approved within predicted timelines | SIP will provide a more predictable timeline once fully implemented. Timelines are less variable and more consistent. HRA Approval report provides more analysis (appendix)
Streamlining processes for researchers | The full elapsed time for a valid application to receive HRA approval from receipt date of original submission | Timelines within target range set | All Approvals timelines met for REC studies. Non REC studies – timelines remain outside 15 day target.

## Slide 8: Making it easier to conduct high quality research in the UK
Chart: 
| 42826 | 42856 | 42887 | 42917 | 42948 | 42979 | 43009 | 43040 | 43070 | 43101 | 43132 | 43160 | 43191 | 43221 | 43252 | 43282 | 43313 | 43344 | 43374 | 43405 | 43435 | 43466 | 43497 | 43525
 | 22 | 28 | 28 | 30 | 22 | 28 | 23 | 16 | 24 | 24 | 17 | 11
 | 11 | 15 | 16 | 19 | 26 | 15 | 24 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Chart: 
| 42826 | 42856 | 42887 | 42917 | 42948 | 42979 | 43009 | 43040 | 43070 | 43101 | 43132 | 43160 | 43191 | 43221 | 43252 | 43282 | 43313 | 43344 | 43374 | 43405 | 43435 | 43466 | 43497 | 43525
 | 8 | 9 | 6 | 7 | 7 | 6 | 6 | 4 | 6 | 7 | 4.5 | 4
 | 4 | 3 | 1 | 2 | 6 | 5 | 6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Chart: 
| 42826 | 42856 | 42887 | 42917 | 42948 | 42979 | 43009 | 43040 | 43070 | 43101 | 43132 | 43160 | 43191 | 43221 | 43252 | 43282 | 43313 | 43344 | 43374 | 43405 | 43435 | 43466 | 43497 | 43525
 | 6 | 7 | 6 | 9 | 5 | 2 | 3 | 2 | 2 | 6 | 1 | 2
 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Chart: 
| 42826 | 42856 | 42887 | 42917 | 42948 | 42979 | 43009 | 43040 | 43070 | 43101 | 43132 | 43160 | 43191 | 43221 | 43252 | 43282 | 43313 | 43344 | 43374 | 43405 | 43435 | 43466 | 43497 | 43525
 | 8 | 10 | 8 | 13 | 6 | 5 | 2 | 4 | 5 | 7 | 5 | 1
 | 1 | 5 | 2 | 1 | 8 | 3 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10

## Slide 9: Making it easier to conduct high quality research in the UK
Model non commercial agreement published
Integrated process for QC and QA implemented in September
New project set up to consider Sponsor level IG standards, including Data Protection Impact Assessment/risk assessment (DPIA) template guidance
Joint HRA/MHRA statement on electronic consent published
Board agreed work to support social care research through information and training and increased HRA expertise

## Slide 10: Making it easier to conduct high quality research in the UK
Theme | Description | Measure | Update
Customer satisfaction | Capturing customer feedback on a more regular basis for specific aspects of the service to establish their overall level of satisfaction. | > 75% of applicants scoring the overall service at 7 or greater on a scale of 1-10 | Qtr2 82% - applicants scoring overall service highly (up 5% from Qtr1) Customer charter published.
Advice and guidance | Our ability to increase the number of application which are ‘right first time’ | Reduction in the number of applications received by HRA with missing documentation | Significantly improved following introduction of verification tool in Spring 2018 – approximately 24% Qtr2 (down 4% from Qtr1).

## Slide 11: Making it easier to conduct high quality research in the UK
Chart: 
| 42826 | 42856 | 42887 | 42917 | 42948 | 42979 | 43009 | 43040 | 43070 | 43101 | 43132 | 43160 | 43191 | 43221 | 43252 | 43282 | 43313 | 43344 | 43374 | 43405 | 43435 | 43466 | 43497 | 43525
 | 0.36 | 0.37 | 0.4 | 0.37 | 0.34 | 0.37 | 0.37 | 0.39 | 0.29 | 0.34 | 0.32 | 0.29
 | 0.29 | 0.28 | 0.26 | 0.3 | 0.25 | 0.28 | 0.2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Slide 12: Making it easier to conduct high quality research in the UK
11/16 applications received are now complete as part of the Combined Ways of Working pilot with MHRA
Four Nations policy leads agreed to roll out, UK wide, local information template
Meeting with HTA to discuss progressing public trust and confidence in collection and sharing of tissue and data
Development of training related to student research findings
Volunteer recruitment - a targeted recruitment campaign pilot in September aimed at clinicians in the Liverpool region

## Slide 13: Develop a pro-active, strategically focussed organisation
Theme | Description | Measure | Update
Engagement | Ensuring senior management are ambassadors for our engagement strategy and staff are encouraged to see engagement with external stakeholders as part of their work | HRA executives spending at least 20% of their time engaging with external stakeholder groups, managing relationships. >50% of our people have an opportunity to interact outside their direct HRA role with research community | 20% of executives time spent engaging with external stakeholder groups and managing relationships. (Down from 25% in previous quarter) 50% of our people have had an opportunity to interact outside their direct HRA role with research community
Engagement | Understand better | Stakeholder engagement survey | Engagement strategy group agreed to develop an engagement strategy for key policy areas (data-driven technology, public involvement, transparency)

## Slide 14: Capitalising on technological developments
Phase 1 IRAS CTIMPs development progressing at pace with strong user and stakeholder engagement
Phase 2 business case being drafted, funding required
Data driven technologies - meeting held with Indra Joshi (NHS England lead for data-driven tech)
IRAS e-learning module updated in August to include a section about the verification tool
eConsent published and promoted on 20th September
Schedule of Events Cost Attribution Template implemented
IT Infrastructure strategy and roadmap developed

## Slide 15: Ensuring the HRA is governed effectively and provides value for the tax payer
Theme | Description | Measure | Update
Cost utilisation | Reduction in the unit cost of processing each application. Enhancing the HRA forecasting tools to deliver a balanced I&E position Improving facilities utilisation and cost effectiveness. Our corporate services compare favourable with industry benchmarks. | >5% cost reduction on 16/17 baseline Divisional forecasts to be within 4% target range Achieve 8sqm / desk industry benchmark and work towards 8:10 ratio of desks / wte Costs equal to industry benchmarks | 2017/18 outturn – breakeven. Forecast costs currently within target range. Currently 8:07sqm/desk. Subletting Manchester will reduce this to within the benchmark. Calculations being developed as part of corporate SIP.

## Slide 16: Ensuring the HRA is governed effectively and provides value for the tax payer
Theme | Description | Measure | Update
Staff engagement | Staff engagement Our commitment to developing our people Our commitment to supporting our people with the IT tools that they need | >80% from annual survey 100% of our eligible people have had at least one appraisal within a 12 month period. 10% improvement on 2018 staff survey response for IT service | Staff survey planned for Qtr4 85% of appraisals completed by September 2018. Staff survey planned for Qtr4. Detailed response to SOCITM survey to help address immediate concerns where possible.

## Slide 17: P6 Finance report