## Sheet1
HRA KPIs, Quarter 1 - 4 2016 / 2017
Ref | Description | Owner | Schedule | Measure | Quarter 1 |  |  | Quarter 2 |  |  | Quarter 1 | Quarter 2
| Operations and CAG |  |  |  | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | Comments (max 228 characters) | Comments (max 228 characters)
A1 | 95% of applications to full research ethics committee meetings to receive final decision within 60 calendar days (mandatory) FIG 1 | JK | Monthly | % | 99.41% | 100% | 99.71% | 99.69% | 99.03% | 100% | Excellent perofrmance maintained | Excellent performance maintained
A2 | 95% of applications to full research ethics committee meetings to receive final decision within 40 calendar days (stretch target) FIG 2 | JK | Monthly | % | 87.94% | 93.31% | 89.47% | 85.94% | 89% | 89.5% | Amendment backlog work commenced in June and staff divrted to assist | Good timelines. Diversion of resources to assist with amendment workload anticipated to have impact on stretch targets. Higher levels of leave in summer months and increased sickness absence.
A3 | 95% of applications to research ethics proportionate review service to receive decision within 14 calendar days FIG 3 | JK | Monthly | % | 80.95% | 85.71% | 92.31% | 87.8% | 90.16% | 89.2% | Problems with booking applications a long way ahead of closing dates due to volume/bank holidays in Apil and May. Work ongoing with UK colleagues to increase proportionate review workload | Diversion of resources to assist with amendment workload anticipated to have impact. Higher levels of leave in summer months and increased sickness absence. Bank Holiday in August.
A4 | 95% of amendments, on approved applications, submitted to research ethics committees to receive a decision within 28 calendar days (stretch target) FIG 4 | JK | Monthly | % | 92.82% | 91.19% | 90.72% | 91.78% | 89.91% | 90.1% | 0 | Good timelines. Diversion of resources to assist with amendment workload anticipated to have impact on stretch targets. Higher levels of leave in summer months and increased sickness absence.
A5 | 95% of amendments, on approved applications, submitted to research ethics committees to receive a decision within 35 calendar days (mandatory) FIG 5 | JK | Monthly | % | 99.24% | 99.25% | 98.67% | 99.29% | 97.66% | 97.9% | Excellent performance maintained | Excellent performance maintained
A6 | 100% of GTAC applications to be receive a decision in 60 days | JK | Monthly | % | N/A | 100% | 100% | 100% | 100% | 100% | 0 | Excellent performance maintained
A7 | CAG/CAT – 75% of full applications to be completed in 60 days FIG 6 | JM | Monthly | % | 77.78% | 100% | 100% | 87.5% | 100% | 81.8% | Some delays caused by member availability over summer period in assessing follow-up responses to provisional/conditional outcomes | Exceptions due to members responding to non-active email address. Ongoing discussions with Chair/officials to discuss member handling of applicant follow-up responses.
A8 | CAG/CAT 75% of Precedent Set review applications to be completed in 30 days FIG 7 | JM | Monthly | % | 0% | 75% | 100% | 66.67% | 100% | 100% | Small number of PS applications reached final approval in July-16; one application considered in 39 days which led to drop in KPI. To be raised with CAG to identify improved efficiencies in member responses to follow-up
A9 | CAG/CAT 75% of amendments to be completed in 30 days | JM | Monthly | % | N/A | 0% | 18.18% |  | 0% |  | Data relating to CAG Amendments may require data cleansing and the figures provided here may be subject to revision in the future. | New spreadsheet developed September 2016 to ensure recording issues prevented. Significant work required to re-populate previous amendment data. 1 amendment closed this month in 32 days. Delay caused as delay from lead official in concluding outcome. Discussions are taking place with officials regarding timeliness of responses.
A12 | Reduction in the number of Provisional Opinions at First Review | JK | Monthly | % | 63.34% | 63.14% | 58.8% | 57.86% | 63.2% | 61.2% | 0 | PR pilot etending timelines showing small but not significant reduction in provisional opinions
A13 | Reduction in the number of Queries raised as a result of REC Review. | JK | Monthly | [7 empty] | 0 | 0 | bar: 2016-04-01 to 2016-09-01
A14 | Reduction in the number of Amendments being processed before a study recruits its first participant. | JK | Monthly | [7 empty] | 0 | 0 | bar: 2016-04-01 to 2016-09-01
HRA Approval
A15 | Non-REC studies: Approved studies (non-REC) are approved in Median 15 days from date of application to the HRA to the date of approval. | JM | Monthly | Median 15 | 27 | 32 | 28 | 51 | 54 | 82 | 0 | Worsening figure in Q2 reflects impact of clearing backlog of amendments and pre-Approval, and focus on clinical studies. Case load management balances progressing new studies vs open studies.
A16 | REC-PR studies: Approved studies (REC-PR) are approved in median 10 days from date of additional REC conditions being met to date of approval. | JM | Monthly | Median 10 | 18 | 20 | 29 | 41 | 40 | 49 | 0 | Worsening figure in Q2 reflects impact of clearing backlog of amendments and pre-Approval, and focus on clinical studies. Case load management balances progressing new studies vs open studies.
A17 | Full-REC, non-Commercial studies (NC Full REC) Approval studies are approved in a median 25 days from the date of final REC Opinion additional REC conditions being met to the date of approval. | JM | Monthly | Median 25 | 8 | 13 | 18 | 26 | 33 | 31 | 0 | Although figures exceed KPIs, median timelines have reached plateau. Important to note that many of these studies would have had a significant time gap between REC and R&D applications, as well as gaps prior to SSI submission, as well as the R&D review process.
A18 | Full-REC, Commercial studies (C Full REC) Approval studies are approved in a median 10 days from the date of final REC Opinion additional REC conditions being met to the date of approval. | JM | Monthly | Median 10 | 10 | 6 | 8 | 13 | 19 | 15 | 0 | Although figures exceed KPIs, median timelines have reached plateau. Commercial applicants have historically made REC and R&D applications in closer sequence than non-commercial, but frequently reported delays in SSI submission by site staff, as well as the R&D review process.
Fig 1
Fig 2
Fig 4
Fig 5
Fig 6
Fig 7
Fig 3
Note on E4: 90% = Red 92% = Amber 95% + = Green
Note on E5: 75% = Red 85% = Amber 95% + = Green
Note on E6: 90% = Red 92% = Amber 95% + = Green
Note on E7: 75% = Red 85% = Amber 95% + = Green
Note on E8: 90% = Red 92% = Amber 95% + = Green
Note on E9: Red = 90 Amber = 95 Green = 100
Note on E10: Red - 25 Amber = 50 Green - 75
Note on E11: Red - 25 Amber = 50 Green - 75
Note on E12: Red = 25 Amber = 50 Green =75