## Sheet1
Activities / Dates | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01
SIP HRA Approval
Integrated Process
Amendments
Proportionality
Get it right first time
Volunteer recruitment and management | 2018-02-01: All Staff VC
PIER
Customer Support
Corporate SIP
|  |  |  | Legend |  | 67
Dependencies
Process/Activity - progressing to plan
Process/Activity - problem being managed by project team but TB need to be aware of
Process/Activity - significant issues that requires the intervention of TB to resolve
Process/Activity - complete
Decision point
Milestone
Go Live
Report of baseline and recommendations for improvements
Customer support
implementation plan
Customer Charter
CRM Software
Pilot/supplementary PI Guidance for applicants
PI Information added to Defining Research Table
Evaluation/review of take up/adherence to guidance
1-2 360 PI case studies
Refine PI guidance and develop resources for applicants and RECs
Refine PI information requirements and develop PI standards/expectations
PI Learning tools and training for RECs
Verification Tool/IRAS form
Review of HRAs's approach to proportionality report
Amendments Review Spec
DA decision on QA QC pilot 18/2
Ready for review process (incl Threshold) tested, evaluated and agreed
Approval finalisation process tested, evaluated and agreed
QC process Evaluation
Review of Amendments Report
Integrated process for HRA
Approval
Amendments integrated process
e-Submission of amendments
DA key
decisions
Re-developed PI content and materials on HRA website
Windows 10, Office 2016
All Staff VC
Facilities and Office Support audit and plan
Absence management policy
IT User List - establish current state, introduce
proces for updating
Employee Self Service (limited) rollout and ESR manager pilot
ESR roll out - manager and further utilisation of functionality to support automation of people processes
End to end people support process implemented
Facilities Support implemented
Estates Strategy agreed
All Staff VC
Information management strategy developed and
agreed
Information management implemented
IM strat imp plan agreed
IT strategy and Road map agreed
IMS3 replacement plan agreed
Steering Group kick off call
Single site at sponsor site studies report
Pilot accreditation scheme and
new QC process
QC process
Live
QC process Decision
Project Brief
Briefing to stakeholders on
outcome of proportionality report
UK wide feedback
Members expenses pilot
Volunteer recruitment plan
Clear Volunteer recruitment
current backlog
Volunteer recruitment pilot for Liverpool
Broader recruitment campaign
Evaluation of expenses pilot
Induction (new starters) discovery work
Managers Handbook Phase 1
Project brief for Amendments
Further UK feedback
Set up working group to develop process
Getting feedback
Develop end to end Integrated process plan
Develop end to end Integrated process SOPs
Pilot
evaluation
Induction (new starters)
Implementation
Proposed Amendments process
Gatekeeping process for email accounts
Guide Framework for responding to customers
Publication of Cust Charter